## Planning
Staff name | Estimated hours | Programme leader | Project code | Project name | Type of analysis (eg RNAseq, variant calling, genome assembly, …) | Any milestone depending on bioinformatics analysis and when is it due?
Amali Thrimawithana | 50 | Susan Thomson | P/471778/13 | Grape assembly | Assembly | yes, 30/6/2017
Amali Thrimawithana | 450 | Jia-Long Yao/Susan Thomson | p/150152/01 | China R Gala & Navel Orange Genome | genome assembly, annotation, comparative genomics | Yes, 30/09/17, 30/12/17, 30/03/18 and 30/06/2018
Amali Thrimawithana | 50 | Jo Bowen | P/312005/01 | Durable Resistance | RNAseq (differential expression) and informed gene prediction of Neonectria: mentoring and helping Brogan McGreal | Yes, likely 30/6/2018 (already ongoing)
Amali Thrimawithana | 100 | Jo Bowen | P/112005/01 | ? | RNAseq (differential expression): mentoring and helping Shakira Johnson | ?
Amali Thrimawithana | 170 | Kathy Schwinn | funding ended | 1476 DS manuka | genome analysis/paper preparation; RNA-seq/DE-seq | no milestones but genome paper is seen as a priority
Amali Thrimawithana | 120 | Kathy Schwinn | TBA | red kiwifruit trait | RNA-seq/DE-seq | before 31 Dec 17
Ben Warren | 96 | Guy Davenport | p/111444/24 | Kiwifruit data registry | Help with iRods configuration | Yes , 30/6/2018
Ben Warren | 560 | Claudia Lang/John Ingram | to be assigned | DS17-15 Noncoding RNAs and human interactome | noncoding RNA analysis and modeling with the human interactome | Yes, 30/06/2018
Ben Warren | 200 | Helge Dzierzon | TBA | Machine learning |  | Yes
Amali Thrimawithana | 50 | Jo Bowen | P/312005/01 | Durable Resistance | PacBio assembly of Venturia and Neonectria genomes: mentoring and helping Linda Collard | Yes, likely 30/6/2018
Cecilia Deng | 150 | Jia-Long Yao/Susan Thomson | p/150152/01 | China R Gala & Navel Orange Genome | genome assembly, annotation, comparative genomics | Yes, 30/09/17, 30/12/17, 30/03/18 and 30/06/2018
Cecilia Deng | 200 | Jo Bowen | P/312005/01 | Durable Resistance | genome assembly: re-sequencing Neonectria progeny for BSA analysis | Yes, likely 30/6/2018
Charles David | 100 | Susan Thomson | None yet | DS17-52 Haplo-tagging polyploids | Simulation testing | Yes, likely 30/6/2017
Charles David | 300 | Jia-Long Yao/Susan Thomson | p/150152/01 | China R Gala & Navel Orange Genome | genome assembly, annotation, comparative genomics | Yes, 30/09/17, 30/12/17, 30/03/18 and 30/06/2018
Charles David | 100 | David Brummell | P/271036/01 | Perfect Fruit (apple series) | RNAseq (differential expression) | No, but critical for identifying targets for milestone due July 2018
Charles David | 100 | David Brummell | P/271036/01 | Perfect Fruit (kiwifruit series) | RNAseq (differential expression) | No, but critical for identifying targets for milestone due July 2018
Charles David | 100 | Ross Lill | P/499000/15 | CORE covered crops (Angel tomato series) | RNAseq (differential expression) | Yes Milestone due 30/6/2018
Charles David | 300 | Jason Johnston | P/274111/01 | Juicy Futures (Smitten) | RNAseq (differential expression) | No, but is well overdue
Charles David | 300 | Don Hunter |  | Confidential | pseudochromosome assembly of 1.4 Gb genome | dependent on client approval of proposal
Charles David | 150 | Don Hunter |  | Confidential | RNAseq (cold tolerance, differential expression) | dependent on client approval of proposal (July 2018?)
Charles David | 50 | Maren Wellenreuther | p/532008/01 | Accelerated breeding for enhanced seafood production | Assistance with trevally genome assembly and annotation | yes, 2017/18
Charles David | 200 | Helge Dzierzon | TBA | Machine learning |  | Yes
Dan Jones | 280 | Claudia Lang/John Ingram | to be assigned | DS17-15 Noncoding RNAs and human interactome | noncoding RNA analysis and modeling with the human interactome | Yes, 30/06/2018
Dan Jones | 100 | Kathy Schwinn | funding ended | 1476 DS manuka | genome analysis/paper preparation | no milestones but genome paper is seen as a priority
Helge Dzierzon | 50 | Susan Thomson | None yet | DS17-52 Haplo-tagging polyploids | Data curation/advisor | Yes, likely 30/6/2017
Helge Dzierzon | 150 | Kevin Davies | P/180100/01 | Primocane | genome assembly, annotation, training Rubina | Yes
Helge Dzierzon | 350 | Helge Dzierzon | TBA | Machine learning |  | Yes
Helge Dzierzon | 350 | Helge Dzierzon | TBA | Machine learning |  | Yes
Marcus Davy | 200 | Susan Thomson | None yet | DS17-52 Haplo-tagging polyploids | Simulation testing, visualisation | Yes, likely 30/6/2017
Marcus Davy | 200 | Samantha Baldwin | P/190501/01 | Smart culling | Simulations
Marcus Davy | 70 | Maren Wellenreuther | p/532008/01 | Accelerated breeding for enhanced seafood production | Trevally transcriptome and help with trevally genome annotation | yes, 2017/18
Ross Crowhurst | 50 | Maren Wellenreuther | p/532008/01 | Accelerated breeding for enhanced seafood production | Snapper genome assembly refinement and write up | yes, 2017/18
Roy Storey | 195 | Maren Wellenreuther | p/532008/01 | Accelerated breeding for enhanced seafood production | Trevally genome assembly and annotation and write up | yes, 2017/18
Roy Storey | 200 | Helge Dzierzon | TBA | Machine learning |  | Yes
Susan Thomson | 50 | David Chagne | p/150199/01 | MBIE LCR Honey Landscape | Variant calling | Yes, 30/06/2018
Susan Thomson | 200 | Susan Thomson | None yet | DS17-52 Haplo-tagging polyploids | Variant calling, haplotyping | Yes, likely 30/6/2017
Susan Thomson | 15 | Susan Thomson | P/471778/13 | Grape assembly | Assembly | yes, 30/6/2017
Susan Thomson | 200 | Samantha Baldwin | P/190501/01 | DS Clever Culling | Variant analysis and polyploid genetics haplotypoping help | Yes, 30/12/2017 and 30/6/2018
Susan Thomson | 100 | Samantha Baldwin | TBA | DS Pretrained for climate change | Methylation analysis development and post-doc mentor | Yes not decided yet
Susan Thomson | 150 | Steve Lewthwaite | P/115002/03 | potato molecular breeding | Variant analysis, SNP checking and manuscript preparation | Yes , 30/6/2018
Susan Thomson | 130 | Helge Dzierzon | TBA | Machine learning |  | Yes
Tim Millar | 200 | Susan Thomson | None yet | DS17-52 Haplo-tagging polyploids | Pipeline development, data curation | Yes, likely 30/6/2017
Tim Millar | 50 | Susan Thomson | P/471778/13 | Grape assembly | Assembly | yes, 30/6/2017
Tim Millar | 200 | Helge Dzierzon | TBA | Machine learning |  | Yes

## Staff list
Name | Location
ROSS CROWHURST | AK
MARCUS DAVY | TP
CECILIA DENG | AK
HELGE DZIERZON | PN
SUSAN THOMSON | LN
ROY STOREY | TP
AMALI THRIMAWITHANA | AK
BEN WARREN | AK
CHARLES DAVID | LN
TIM MILLAR | LN
DAN JONES | AK
CHEN WU | AK